{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["QTE","CALCOLO spese tecniche interne"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"QTE","index":0,"n_rows":58,"n_cols":11,"rows_kept":58,"cut":false,"hidden":false,"merged":[[0,0,0,9],[4,9,5,9],[4,7,5,7],[54,0,54,6],[2,0,2,9],[1,0,1,9],[3,0,3,8],[4,1,5,1],[4,8,5,8]],"flags":["formulas_cached_only"]}
["Allegato a determinazione n° 872 del 11.09.2018"]
["REALIZZAZIONE DI NUOVO  EDIFICIO PER SERVIZI SOCIOASSISTENZIALI in VIA DELLE INDUSTRIE"]
["ALLACCIO UTENZA ELETTRICA SOCIETA' IREN MERCATO DI GENOVA"]
["tranche 2016"]
["voce","valore netto iva","ci","iva","iva","orr","irap","totale","data prestazione","pagamenti"]
[null,null,0.04,0.1,0.22,0.238,0.085]
[]
["opere a base d'asta",398888.21,null,39888.821,null,null,null,438777.031]
["% ribasso",25.889]
["Ribasso",103268.16868690001]
["Importo ribassato",295620.0413131,null,29562.004131310005,null,null,null,325182.04544441]
["oneri sicurezza",19640,null,1964,null,null,null,21604]
[315260.0413131]
[]
["Progettazione Preliminare Det. n. 536 del 29,06,2016 €. 2.850,00 + 4% + 22% (€.3.616,08 sul Cap. 10012)"]
[]
["Spesa esigibile nel 2016"]
["Progettazione Def-Esec Det. n. 911 del 24,10,2016 - Cap. 11755",20790,831.6,null,4756.7519999999995,null,null,26378.352,"2016-10-31","2016-12-31"]
["Direzione Lavori, Contabilità, CRE e Sicurezza (€.21.000,00+4%+22%) a carico ARCA",null,0,null,0,null,null,0]
[null,"Sub-Totale",{"$nulls":5},26378.352]
[]
["Spesa esigibile nel 2017"]
["Lavori",155300,null,15530,null,null,null,170830,"31,12,2017","31,12,2017"]
["Versamento S.A. Anac",225,{"$nulls":5},225,"30,03,2017","30,03,2017"]
["Accantonamento innovazione tecnologica  - art. 113/D.lgs 50 su opere a ba",1674.11,{"$nulls":5},1674.11,"31,12,2017","31,12,2017"]
[null,"Sub-Totale",{"$nulls":5},172729.11]
[]
["Spesa esigibile nel 2018"]
["Lavori:",140320.04131310002,null,14032.004131310003,null,null,null,154352.04544441003,"30,09,2018","2018-10-31"]
["Oneri sicurezza ",19640,null,1964,null,null,null,21604,"30,09,2018","2018-10-31"]
["Spese tecniche ex art. 113/Dlgs 50 su opere a b.a.",5409.085,null,null,null,1287.36223,459.77222500000005,7156.2194549999995,"2018-09-30","2018-12-31"]
[]
["Opere perizia  n° 1 ",20499.87,null,2049.9869999999996,null,null,null,22549.857,"30,06,2018","2018-10-31"]
["Sicurezza perizia n° 1",1078,null,107.8,null,null,null,1185.8,"30,06,2018","2018-10-31",23735.657]
[]
["Opere complementari P.T. Arca",61238.28,null,6123.828,null,null,null,67362.108,"30,06,2018","2018-10-31"]
["Sicurezza Op. Compl",5274.29,null,527.429,null,null,null,5801.719,"30,06,2018","2018-10-31"]
["Spese tecniche ex art. 113/Dlgs 50 su opere complementari",859.613182552504,null,null,null,204.58793744749596,73.06712051696285,1137.2682405169628,"2018-09-30","2018-12-31"]
["Acc. Innovaz.tecn. art. 113/D.lgs 50 su opere complementari",266.05027999999993,{"$nulls":5},266.05027999999993,"2018-12-31","2018-12-31"]
["Allacciamento acqua/Uniacque",402.5,null,40.25,null,null,null,442.75,"30.05.2018","2018-09-30"]
["Allacciamento gas/2iRete Gas",561.83,null,null,123.6,null,null,685.4300000000001,"30.05.2018","2018-09-30"]
["Scavo allacciamento H2O (Fratus)",1501.81,null,150.18099999999998,null,null,null,1651.991,"2018-07-15","2018-09-30"]
["Anac",30,{"$nulls":5},30,"2018-06-30","2018-09-30"]
["Allacciamento Iren Mercato s.p.a.",1764.7,null,null,388.23,null,null,2152.9300000000003,"2018-09-20","2018-09-30"]
["Somme a disposizione per altre opere da allacciamento delle utenze",580.34,null,null,127.67480000000002,null,null,708.0148,null,null,80238.26132051693]
[]
["Opere perizia n.2 sistemazione piazzale e posa siepe",7517.8,null,751.78,null,null,null,8269.58,"2018-09-30","2018-10-31"]
["Sicurezza Op. perizia n° 2 piazzale e siepe",663,null,66.3,null,null,null,729.3,"2018-09-30","2018-10-31",8998.88]
[]
[]
["Spese tecniche collaudo Ing. Algeri",3588.36,143.5344,null,821.016768,null,null,4552.9111680000005,"2018-09-30","2018-10-31"]
["Imprevisti comprensivi del ribasso \n(post perizia e post opere compelmentari)",231.42,null,23.142,null,null,null,254.56199999999998]
[null,"Sub-Totale",{"$nulls":5},300892.53638792696]
[]
["TOTALE QTE ulteriormente rideterminato, in aggiornamento ex Det. n. 731/2018",{"$nulls":6},499999.99838792696]
[]
[{"$nulls":7},"Il Responsabile dell'Area III-IV"]
[{"$nulls":7},"Arch. Alberto Nicolo'"]

{"sheet":"CALCOLO spese tecniche interne","index":1,"n_rows":25,"n_cols":5,"rows_kept":25,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
["OPERE A BASE D'ASTA",null,"OPERE PRINCIPALI"]
[418528.21,0.02,8370.5642]
[null,null,6696.451360000001,1674.1128399999998,"F. DO ACC.TO….."]
[null,null,"80% incl. oorr escl.irap",0.2]
[null,null,"SP. TECNICHE"]
[]
[null,"SP.TEC IMP",5409.088336025849,"netto oorr"]
[null,"ORR 23,%",1287.3630239741522]
[null,"IRAP 8,5%",459.7725085621972]
[]
[]
[]
[]
[]
["OPERE A BASE D'ASTA",null,"OPERE COMPLEMENTARI"]
[66512.56999999999,0.02,1330.2513999999999]
[null,null,1064.20112,266.05027999999993,"F. DO ACC.TO….."]
[null,null,"80% incl. oorr escl.irap",0.2]
[null,null,"SP. TECNICHE"]
[]
[null,"SP.TEC IMP",859.613182552504,"netto oorr"]
[null,"ORR 23,%",204.58793744749596]
[null,"IRAP 8,5%",73.06712051696285]