{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["1° E 2° MESE"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"1° E 2° MESE","index":0,"n_rows":20,"n_cols":62,"rows_kept":20,"cut":false,"hidden":false,"merged":[[7,16,7,22],[7,72,7,78],[7,79,7,85],[7,58,7,61],[7,51,7,57],[6,58,6,61],[6,30,6,57],[0,0,5,29],[6,0,8,0],[6,1,8,1],[7,65,7,71],[7,30,7,36],[7,37,7,43],[7,9,7,15],[7,23,7,29],[7,2,7,8],[6,2,6,29]],"flags":["formulas_cached_only"]}
["COMUNE DI POGGIO RUSCO\nREALIZZAZIONE DI UN PERCORSO DI ACCESSO AD IMPIANTO DI SOLLEVAMENTO\n SU TERRENI DI PROPRIETA' PRIVATA\n\nCRONOPROGRAMMA DEI LAVORI"]
[]
[]
[]
[]
[]
["Fase","  DURATA                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                        \n                                                                                    LAVORAZIONE                                                                                                                                                          ","MESE 1",{"$nulls":27},"MESE 2",{"$nulls":27},"MESE 3"]
[null,null,"1° SETTIMANA",{"$nulls":6},"2° SETTIMANA",{"$nulls":6},"3° SETTIMANA",{"$nulls":6},"4° SETTIMANA",{"$nulls":6},"5° SETTIMANA",{"$nulls":6},"6° SETTIMANA",{"$nulls":6},"7° SETTIMANA",{"$nulls":6},"8° SETTIMANA",{"$nulls":6},"9° SETTIMANA"]
[null,null,"L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G","V","S","D","L","M","M","G"]
[]
[1,"PULIZIA AREA DI CANTIERE DA VEGETAZIONE"]
[2,"SCAVO DI SBANCAMENTO E ACCATASTAMENTO MATERIALE"]
[3,"FORNITURA E POSA DI GEOTESSUTO"]
[4,"FORNITURA E POSA STRATO DI VAGLIATO/RICICLATO"]
[5,"COMPATTAZIONE STRATO DI VAGLIATO/RICICLATO"]
[6,"FORNITURA E POSA STRATO DI STABILIZZATO"]
[7,"COMPATTAZIONE STRATO DI STABILIZZATO"]
[8,"SCAVO E GETTO DEI PLINTI DI FONDAZIONE"]
[10,"FORNITURA E POSA DI RECINZIONE METALLICA E PORTONE"]
[null,null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60]